## 文档使用说明
1、每个访谈角色按自己的情况进行回答
2、每个被访谈人员都需要填写一下（只填写各自对应的 Sheet页），结合自己的实际工作来填写，回答的时候参考“标准过程”里面各自对应过程文档中的“过程”和“指南”中的内容（流程 和 活动说明部分）
3、角色对应内容：
角色名称 | 角色说明 | 公共部分 | 自己的Sheet页 | 对应的过程文档 | 相关的输出文档
EPG | 过程改进组 | 公共实践GP | EPG | 组织定义与过程改进（OPD、OPF） | 组织过程改进、组织资产库
QA | 质量人员 | 公共实践GP | PPQA | 质量保证（PPQA） | 过程改进中的质量保证、各个项目中的质量保证
CM | 配置管理 | 公共实践GP | CM | 配置管理（CM） | 过程改进中的配置管理 和 组织基线、各个项目中的配置管理 和 项目基线
OT | 培训专员 | 公共实践GP | OT | 组织培训（OT） | 组织资产库 中的 组织培训部分
PM | 项目经理 | 公共实践GP | PM | 项目管理类（立项结项、项目计划-PP、项目监控-PMC、度量分析-MA、风险管理-Resk、集成项目管理-IPM、决策分析-DAR、产品集成-PI、同行评审-VER） | 各个项目中的 管理域 部分、工程文档中的计划部分
RDM | 需求人员 | 公共实践GP | Req.Anal | 需求开发与管理（RD、REQM）、同行评审（VER） | 各个项目中 工程文档的需求部分、管理文档中的需求评审、需求变更或配置管理中的变更部分
Engineer | 设计开发 | 公共实践GP | Engineer | 决策分析（DAR）、技术解决方案（TS）、同行评审（VER）、产品集成（PI） | 各个项目中 工程文档的设计部分、管理文档中的设计评审、集成测试部分的接口文档、编码实现中的所有文档、用户手册
Tester | 测试人员 | 公共实践GP | Tester | 验证（VER）、确认（VAL）、同行评审（VER） | 各个项目中的 工程文档的 测试部分、验收部分，管理文档中的 评审文档部分

## 公共实践（所有人都需要回答）GP
序号 | 实践 | 关联的过程域 | 访谈问题 | 结合各自角色自身来回答 | 各自角色对应的文档证据
GP2.1 | 建立组织级方针 Establish an Organizational Policy | OPD | 如何知道组织级的方针，请举例说明。 Do you know the org policies? Give some examples, please. 与你相关的过程域（制度）的目的是什么？
GP2.2 | 计划过程 Plan the Process | PP | 如何制定了该过程的计划？在哪里记录？ Do you make the plan for this process? Where does it record?
GP2.3 | 提供资源 Provide Resources | PP SP2.4 | 实施该过程用到了哪些资源？， 如工具，设备，资金等？ Which resources do you use for implementing this process, such as tools, equipments, or money?
GP2.4 | 分配职责 Assign Responsibility | PP SP2.4 | 你的职责是什么？如何清楚定义？ What's your roles and responsibilities in this process, where are they defined?
GP2.5 | 培训人员 Train People | OT PP SP2.5 | 都参加过哪些培训？ What kind of trainings did you get?
GP2.6 | 控制工作产品 Control Work Products | CM | 该过程有哪些产出物？请举例说明。对产出物如何管理？ Please give me some examples for the outputs of this process, and how to manage the outputs?
GP2.7 | 标识并使相关人员参与 Identify and Involve Relevant | PP SP2.6 PMC SP1.5 IPM SP2.1 | 都有哪些人参与到了此项活动中？ Who are involved in this process?
GP2.8 | 监控和控制过程 Monitor and Control the Process | PMC、MA | 如何监控该过程的实施？ How to monitor the implementation of this process?
GP2.9 | 客观评价符合性 Objectively Evaluate Adherence | PPQA | PPQA如何审计过你的工作？怎样审计的？ Did PPQA audit your job? How does he/she audit?
GP2.10 | 和高层经理评审状态 Review Status with Higher Level Management | PMC SP1.6 PMC SP1.7 | 高层有没有参与过评审？ 高层经理是如何关注过程的？ Is the senior manager involved in the review of this process? How does he knows the status of this process?
GP3.1 | 建立已定义过程 Establish a Defined Process | OPD IPM SP1.1 | 该过程有没有做过裁剪？ Does this process have some tailoring?
GP3.2 | 收集过程相关的经验 Collect Process Related Experiences | IPM SP1.7 OPF SP3.4 OPD | 有没提过改进建议？ Did you provide some improvement suggestions?

## Last 2Q
| 过去一年中，你做的最大的改进是什么 What has changed the most over the last year? | 除了你的老板和工资无法改变， 你最想要改进什么？ If you could change one thing, other than your boss or paycheck, what would it be?
Sr.Mgr
PM1
PM2
PM3
Req. Ana1
Req. Ana2
Req. Ana3
Eng.1
Eng.2
Eng.3
Tester1
Tester2
Tester3
CM
EPG
QA
OT

## 高层经理
分类 | 问题 | 访谈记录（高层经理）
OPF | 为什么公司实施过程改进活动 Would you tell me objectives to implement process improvement activities.
PM | 如何关注项目的进度、风险？参与哪些会议？ What is your focus points to the progress of the project, is it a risk? What kind of meeting do you participate?
OT | 如何关注公司的各种培训活动 What is your focus points to the company's various training activities
MA | 如何评审关注公司的度量体系。 How to review the company's metric system.

## 项目经理 PM
| 序号 | 实践 | 访谈问题 | 结合自身实际工作的情况来回答 | 文档证据
Project Planning
| SP1.1 | 估计项目范围 Estimate the Scope of the Project | 你是如何估算项目范围的？ 如何进行任务分解（WBS）？ 分解到什么程度？
| SP1.2 | 建立工作产品和任务属性的估计 Establish and maintain estimates of work product and task attributes. | 如何进行的估计？ How to do estimation? 使用什么估算方法？
| SP1.3 | 定义生命周期 Define Project Life Cycle | 如何定义了项目生命周期？ Did you define the project lifecycle? 你们常用的生命周期模型有哪些？都有什么特点？
| SP1.4 | 确定工作量和成本的估计 Estimate Effort and Cost | 项目工作量是如何估计的？ How to estimate the project working effort? 成本如何估计？
| SP2.1 | 建立预算和进度 Establish the Budget and Schedule | 如何做了项目预算？ 在哪里文档化了？ Do you make the project budget? Where is it documented? 进度计划是怎么制定出来的？
| SP2.3 | 计划数据管理 Plan for Data Management | 哪些项目数据需要管理，在哪里定义了？ Which project data need to be managed? Where are they defined? 项目的输出都有哪些？怎么进行管理？
| SP2.4 | 计划项目资源 Plan for Project's Resources | 项目所需要的资源有哪些？在哪里有说明？ What are the project needed resources, where are they documented?
| SP2.5 | 计划所需的知识和技能 Plan Needed Knowledge and Skills | 项目所需要的知识和技能有哪些，在哪里有说明？ What are the project needed skills and knowledges? Where are they documented?
| SP2.6 | 计划相关人员的参与 Plan Stakeholder Involvement | 识别了哪些干系人？ 在哪里文档化了？ Who are the identified stakeholders? Where are they documented?
| SP2.7 | 建立项目计划 Establish the Project Plan | 如何建立了总体项目计划？ 项目总体计划中包含了哪些子计划？ Do you created the project overall plan? Which sub plans are included in?
| SP3.1 | 评审项目计划 Review Plans that Affect the Project | 如何评审了项目计划？ 都有谁参与了评审？ Are the project plan reviewed? Who are the reviewers?
| SP3.2 | 调整工作和资源 Reconcile Work and Resource Levels | 如何判断项目计划是否可行？ 项目实际可用的资源和估计的资源出现偏差如何处理？ How to judge whether the project plan is feasible? How did you do id the actual available resources can not meet the estimated resources?
| SP3.3 | 获得对计划的承诺 Obtain Plan Commitment | 如何获得干系人对计划的承诺？ How to get the stakeholders commitment for the project plan?
Project Monitoring and Control
| SP1.1 | 监督项目计划各项参数 Monitor Project Planning Parameters | 项目经理监控哪些要素？ What do you monitor in the project? 在执行计划的时候，都会产生哪些数据/数字？
| SP1.2 | 监督承诺 Monitor Commitments | 项目经理怎样监控承诺？ How do you monitor the commitment?
| SP1.4 | 监督数据管理 Monitor Data Management | 如何监控项目数据管理（项目中所有输出的资料）？ How to monitor the data management?
| SP1.5 | 监督相关人员参与 Monitor Stakeholder Involvement | 如何监控项目干系人参与？ How to monitor the stakeholders involvement?
| SP1.6 | 进行进展评审 Conduct Progress Reviews | 如何评审项目进展？ How to review the project progress?
| SP1.7 | 进行里程碑评审 Conduct Milestone Reviews | 如何进行里程碑评审的？ How to conduct the milestone review?
| SP2.1 | 分析问题 Analyze Issues | 收集哪些问题，如何分析？ Which issues are you collected? And how were they analyzed？
| SP2.2 | 采取纠正行动 Take Corrective Action | 怎样采取纠正行动？ How to take corrective actions?
| SP2.3 | 管理纠正行动 Manage Corrective Action | 如何管理纠正行动？ How to manage corrective actions?
Integrated Project Management
| SP1.1 | 建立项目已定义过程 Establish the Project’s Defined Process | 怎样对组织的标准过程进行裁剪来定义出项目自己的过程？ How did you tailor the org standard processes to define the project's processes?
| SP1.2 | 使用组织过程资产计划项目的活动 Use Organizational Process Assets for Planning Project Activities | 项目做计划时使用了哪些组织过程资产，哪些组织级度量数据？ Which process assets and measurement data are used in making the project plan?
| SP1.3 | 建立项目的工作环境 Establish the Project’s Work Environment | 项目的工作环境是如何建立的？ 在哪里文档化了？ How to create the project's working environment? Where is it documented?
| SP1.4 | 集成计划 Integrate Plans | 项目的总体计划包含哪些子计划？ Which sub plans are included in the project overall plan? 这些计划是怎么整合起来的？
| SP1.5 | 使用集成计划管理项目 Manage the Project Using the Integrated Plans | 如何使用集成起来的总体计划管理项目？ How to use the integrated project overall plan to manage project?
| SP1.6 | 建立团队 Establish Teams | 如何建立团队？ 项目团队的组织架构是什么样的？ How to establish a team? What's the structure of a project team?
| SP1.7 | 贡献经验到组织过程资产库 Contribute to the Organizational Process Assets | 项目贡献了哪些经验教训到组织过程资产库中？ What lessons learned or experience collected does project contributes to process asset library?
| SP2.1 | 管理干系人参与 Manage Stakeholder Involvement | 如何管理项目干系人？ How to manage project stakeholders?
| SP2.2 | 管理关键依赖 Manage Dependencies | 如何识别、管理关键依赖？ How to identify and manage the critical dependencies?
| SP2.3 | 解决协作问题 Resolve Coordination Issues | 如何和干系人一起解决问题？ How to resolve issues with stakeholders?
Risk Management
| SP1.1 | 确定风险来源和分类 Determine Risk Sources and Categories | 组织级或你有没有定义风险的来源？ 都有哪些来源？ Does organization(/you) define the risk sources and categories, what are they?
| SP1.2 | 定义风险参数 Define Risk Parameters | 组织级或你有没有定义风险的参数？ 都有哪些参数？ Does organization(/you) define risk parameters? What are they?
| SP1.3 | 建立风险管理策略 Establish a Risk Management Strategy | 组织级或你如何建立了风险管理的策略？ 包含哪些内容？ Does organization(/you) create the risks management strategy? What are they?
| SP2.1 | 识别风险 Identify Risks | 什么时候识别风险？ 如何识别？ When do you identify risks? How to identify?
| SP2.2 | 对风险进行评价、分类和排序 Evaluate, Categorize, and Prioritize Risks | 如何评价风险? How to evaluate the risks?
| SP3.1 | 开发风险缓解计划 Develop Risk Mitigation Plans | 如何缓解风险？ How to mitigate risks?
| SP3.2 | 实施风险缓解计划 Implement Risk Mitigation Plans | 如何跟踪风险? How to track risks? 风险是怎么进行监控的？ 风险发生之后如何进行处理的？
Measurement and Analysis
| SP1.1 | 建立度量目标 Establish Measurement Objectives | 组织或你项目有没有定义出度量目标？ Does Organization(/you) document the measurement objectives? 度量的目标是怎么确定的？
| SP1.2 | 定义度量 Specify Measures | 组织或你项目有没有根据度量目标定义出一些度量项，都有哪些？（基本度量和派生度量） Does Organization(/you) document the measures(base and derived measures) based on the measurement objectives? What measures do you define?
| SP1.3 | 定义数据采集和存储的具体过程 Specify Data Collection and Storage Procedures | 组织或你项目中有没有定义出怎样收集和存储数据？ Does Organization(/you) document how to obtain and store the measurement data? 数据是如何收集，并存储的？ 数据分析的结果又是怎样存储的？ How do you collect and store data including results?
| SP2.1 | 采集度量数据 Obtain Measurement Data
| SP2.3 | 管理度量数据和结果 Store Data and Results
| SP1.4 | 定义分析的具体过程 Specify Analysis Procedures | 组织或你项目中有没有定义出如何分析和汇报度量数据？ 你是怎样进行度量数据的分析的？ Does Organization(/you) document how to analyze and report the measurement data? How do you analyze measurement data according to the procedure?
| SP2.2 | 分析度量数据 Analyze Measurement Data
| SP2.4 | 沟通结果 Communicate Results | 度量数据的沟通途径是怎样的？ How do you communicate the measurement data? 度量的结果是如何使用的？

## SAM (hidden)
序号 | 实践 | 访谈问题 | 考核点
SP1.1 | 确定采购类型 Determine the type of acquisition for each product or product component to be acquired. | 有哪些采购类型？ | 在产品和产品构件采购时，可使用的采购类型举例: 1.购买对项目有重要价值的现货产品，并进行修改 2.通过供应商协议获得产品 3.从内部供应商获得产品 4.从客户处获得产品 5.从最佳供应商名单中获得供应商的产品
SP1.2 | 选择供应商 Select suppliers based on an evaluation of their ability to meet the specified requirements and established criteria. | 如何选择供应商？ | 影响供应商选择的因素举例： 1.供应商的物理位置 2.供应商做相似工作的性能记录 3.工程能力 4.供应商人员和设备的可用性 5.从事类似工作的经验 6.类似项目的客户满意度 选择供应商的基本步骤： 1.建立和维护评价供应商的准则 2.识别潜在的供应商，收集他们的材料和需求（市场调研） 3.根据评价准则评价供应商的提案、能力，并识别供应商相关的风险 4.最终选择供应商
SP1.3 | 建立供应商协议 Establish and maintain supplier agreements. |  | 供应商协议指：组织和供应商之间任何有文字形式的协议，协议的形式可以是合同、许可、服务等级协议、备忘录等。 1.如果合适的话，供应商协议的内容应该安排选择的将进行监控、分析和评价的供应商的过程和产品 2.供应商协义应该指定需要执行的评审、监控、评价和验收测试 3.对项目成败至关重要的供应商的过程应该监控 4.供应商协议需要经过专业法律人士或合同审核员的审核 | 1.当需要时，根据和供应商谈判的结果修改需求 2.文档化项目要提供给供应商的内容，例如设备、文件等 3.文档化供应商协议，包含工作说明、产品规格、约束条款、交付物清单、进度、预算、定义的验收程序 4.定期评审供应商协义，确保它正确的反映了项目和供应商的关系，当前的风险和市场条件。 5.确保在执行供应商协议之前，供应商协议中的各方理解协议中的需求并达成一致 6.
SP2.1 | 执行供应商协议 Perform activities with the supplier as specified in the supplier agreement. | 如何监控供应商？ | 1.按照供应商协议的规定，监控供应商的进展和性能（进度、工作量、成本、技术性能） 2.按照供应商协议的规定，选择、监控和分析供应商使用的过程（选择关键的过程进行监控） 3.按照供应商协议的规定，选择和评价供应商的工作产品（选择关键的工作产品，如早期就能反映质量问题的工作产品，需求、设计文档等）；在低风险的情况下可不用选择任何工作产品 4.按照供应商协议的规定，和供应商一起进行评审（如，里程碑评审、进展评审），可以正式也可以非正式 5.按照供应商协议的规定，和供应商一起进行技术评审（如技术方案、设计评审等） 6.使用评审结果，改进供应商的性能；和优质供应商建立长期的合作关系 7.识别和监控和供应商相关的风险
SP2.2 | 接受采购的产品 Ensure that the supplier agreement is satisfied before accepting the acquired product. | 如何验收采购的产品？ | 接受产品之前应该进行验收测试、配置审计 1.定义验收程序，并和相关干系人评审验收程序，并确保相关干系人对验收程序达成一致 2.验证被采购的工作产品（评审、测试） 3.确保非技术承诺被满足，例如：支持材料、授权许可等可用 4.记录验收结果，并跟踪问题关闭
SP2.3 | 确保产品转移 Ensure the transition of products acquired from the supplier. | 如何进行采购产品移交？ | 1.采购的产品移交给项目、客户、最终用户之前，应该进行合适的准备和评价，确保顺利移交 2.对执行接收、存储、集成、维护采购的产品的人员进行适当的培训，并确保相应的设备可用 3.确保采购产品的存储、分发、集成符合供应商协议中的条款

## 需求人员 Req.Anal
| 序号 | 实践 | 访谈问题 | 结合自身实际工作的情况来回答 | 文档证据
Requirements Development
| SP1.1 | 引导需求 Elicit Needs | 需求的来源有哪些？ Where do requirements come from?
请详细解释如何引出客户的要求。 Please explain in detail on how to elicit the customer requirements.
| SP1.2 | 开发客户需求 Transform Stakeholder Needs into Customer Requirements | 如何文档化了客户需求？ 客户需求是如何划分优先级的？ 如何与客户进行的需求确认？ Have you already documented the customers requirements? How to prioritize customer requirements? How to confirm requirement with customer?
| SP2.1 | 建立产品和产品构件需求 Establish Product and Product Component Requirements | 如何撰写了产品需求规格说明书？ How to make the requirement specification? 规格是什么？
| SP2.2 | 分配产品构件需求 Allocate Product Component Requirements | 你是如何划分产品构件/模块的？ 所有的需求都被分配到了产品构件/模块中吗？ How to allocate products components and modules? Are all of the requirements allocated to product components or modules?
| SP2.3 | 识别接口需求 Identify Interface Requirements | 如何进行接口需求的描述？ Do you have the interface requirements description?
| SP3.1 | 建立操作概念和场景 Establish Operational Concepts and Scenarios | 需求描述时如何从操作概念和场景的角度进行了描述？ Do you have the operating concepts and scenarios? 软件的功能部分的执行过程是如何描述的？ 产品的运行环境是怎样描述的？
| SP3.2 | 建立必须的功能和质量属性的定义 Establish a Definition of Required Functionality and Quality Attributes | 如何确定了功能、性能需求？ Do you define the functional requirements and performance requirements?
| SP3.3 | 分析需求 Analyze Requirements | 需求是如何进行分析的？分析什么？ How to you analyze the requirements, from which aspect to analyze the requirements?
| SP3.4 | 分析需求并达到平衡 Analyze Requirements to Achieve Balance | 如何分析需求相关的风险？ Do you analyze the risks related to requirements?
| SP3.5 | 用综合的方法确认需求 Validate Requirements | 使用了哪些方法确认需求？ Using which methods to validate requirements?
Requirements Management
| SP1.1 | 获得对需求的理解 Obtain an Understanding of Requirements | 需求提供者有哪些？ 如何就需求和需求提供着达成一致理解？ Who are the requirements providers? How to reach a same understanding with the requirements providers?
| SP1.2 | 取得对需求的承诺 Obtain Commitment to Requirements | 如何获得项目参与人员对实现需求的承诺？ How to obtain commitment to requirements from project participants?
| SP1.3 | 管理需求变更 Manage Requirements Changes | 需求变更流程是怎么样的？ What is the process of requirement change? 谁来决定如何执行变更？
变更影响分析哪些内容？ Which information are analyzed for the requirement change impact?
| SP1.4 | 维护需求的双向可跟踪性 Maintain Bidirectional Traceability of Requirements | 如何跟踪需求和之后工作产品的关系？ 建立了哪些跟踪矩阵？ How to track the relationship between requirements and the follow up products? Which requirement traceability matrix is established?
| SP1.5 | 确保项目计划和接下来的工作产品和需求保持一致 Ensure Alignment Between Project Work and Requirements | 需求与项目计划，设计等文档的不一致是如何识别的？ How to identify the inconsistency among requirements and project plan, design and other documents? 在项目的实施及实现过程中，对需求的实现情况，你们是如何跟踪及判断的？

## 设计开发人员 Engineer
| 序号 | 实践 | 访谈问题 | 结合自身实际工作的情况来回答 | 文档证据
Technical Solution
| SP1.1 | 开发详细候选解决方案和选择准则 Develop Alternative Solutions and Selection Criteria | 识别了几个技术方案，如何进行识别的？ How many technical solutions are identify? How to identify? | 1.看客户的具体需求，里面是否要求；2.看公司技术水品，用哪个更加合适；3.可行性分析，从各个角度分析项目的可行性；4.风险性预测。
|  |  | 选择准则及其权重是怎样制定的？ How to make the selection criteria and the weights? | 1.根据客户的具体需求；2.结合公司技术能力；3.考虑到投入，产出和成本；4.看公司的权重是偏向那边还是偏向投入，产出和成本。
| SP1.2 | 选择产品构件解决方案 Select Product Component Solutions | 用什么方法选择技术方案？ Which method do you use to select the technical solution? | 优先对照客户的具体需求，然后结合公司技术能力。看是选择新的技术还是熟悉的技术，同时还要考虑到安全性和保密性。
| SP2.1 | 设计产品或产品构件 Design the Product or Product Component | 如何做设计的？ How do you do design? 整体的设计怎么做？各个功能的设计是怎么做的？ | 1.根据接口规范；用户需求；界面设计规范；技术本身规范；行业规范来做设计；2.整体设计会有一个概要设计说明书，这个里面有功能划分，功能实现，外部接口如何实现；还有一个详细设计说明书，里面就是具体功能实现，内部接口和外部接口的实现。
|  |  | 设计评审是怎么做的？ How do you do the design review? | 1.开会讨论，根据公司技术能力评定设计是否合理，能否完成需求设计文档；然后进行风险预测。如果不能完成的话看备选方法是否可行。
| SP2.2 | 建立技术数据包 Establish a Technical Data Package | 技术数据包包含哪些内容？ 如何使用技术数据包？ What are included in the technical data package? How to use the technical data package? | 一、技术数据包中含有挑选进行实现的所选定与备选解决方案的描述。二、1.1：确定设计层次的数量，以及每一设计层次适当的文档水平；1.2：确定用语进行架构文档化的视图；1.3：将设计的详细描述建立在已分配的产品组件需求、架构与上一级设计的基础上；1.4将设计文档化在技术数据包中；1.5：文档化所做出的或所定义的关键（即：对成本、进度或技术性能产生显著影响的）决策，并包括其依据；1.6：必要时修订技术数据包；
| SP2.3 | 使用准则设计接口 Design Interfaces Using Criteria | 如何设计接口？ How to design interfaces? | 使用所建立的准则设计产品组建的接口
| SP2.4 | 进行制造、购买或复用分析 Perform Make, Buy, or Reuse Analyses | 什么时候做制作、购买、复用分析？ When and how to do the make, buy, reuse analysis? | 自制或购买分析开始于项目早起的第一次设计迭代期间；在设计过程中继续进行；完成于产品的开发、采购或复用的决策。 依据所建立的准则，评价产品组件是应当自行开发、还是购买或者复用
| SP3.1 | 实现设计 Implement the Design | 用什么语言编码？ Which code language do you use? | JAVA,Python,HTML
|  |  | 代码评审是怎么做的？ How do you do the code review? | 1.模块化。2.清晰性。3.简洁性。4.可靠性。5.安全性。6.可维护性
|  |  | 单元测试是怎么做的？ How do you do the unit test? | 单元测试:1. 制定详细的单元测试计划， 2.建立相对独立的单元测试环境；3.根据 实际业务逻辑，设计单元测试用例；4.编写单元测试代码；5.执行单元测试；6.测试时发现问题，及时修改代码，修复缺陷，并做相关记录，包括代码记录（可以在代码中体现，并加以注释）；7.如果修改了代码，应对整个单元进行回归测试
| SP3.2 | 编制产品支持文档 Develop Product Support Documentation | 都编写了哪些用户使用的文档？ Which documents do you provide for the users? | 1.项目估计规范；2.项目开发环境支持活动规范；3.WBS分解作业 指南；4.开发案例编写指南；
Product Integration
| SP2.1 | 评审接口描述的完整性 Review Interface Descriptions for Completeness | 如何保证内外部接口是兼容的？ 如何评审了接口描述？ How to ensure the compatibility for the internal and external interfaces? Do you review the interfaces description? | 1. 确保接口在整个产品生命周期的兼容性。 2. 解决冲突、不符合及变更问题。 3. 维护项目参与人员都能存取的接口数据储存库。一个共享、可存取的接口数据储存库，提供一机制，以确保每人都知道最新接口数据存放处，及其取得和使用。
| SP2.2 | 管理接口 Manage Interfaces | 如何管理接口？ How to manage the interfaces? 接口在什么情况下会变更？ | 1. 审查接口数据的完整性，并确保已涵盖所有接口。 2. 确保产品组件与接口已标识（标注记号），以确保容易与正确的连接产品组件。 3. 定期审查接口说明的充分性。建立接口后，必须定期审查接口说明，以确保现有接口说明与正在开发、处理、生产或购买中的产品并无偏差。产品组件接口说明应与相关干系人共同审查，以避免误解、减少延期，并避免开发无法正常运作的接口。
| SP3.4 | 包装并交付产品或产品构件 Package and Deliver the Product or Product Component | 交付前要准备什么？ 交付的方式是怎样的? 交给客户哪些内容？ Before the deliver, what do you need to prepare? How to deliver? What do you deliver to customer? | 1.提供交付清单（包含功能模块清单）
Verification
| SP2.１ | 准备同行评审 Prepare for Peer Reviews | 如何准备同行评审？ How to prepare the peer review? | 确定评审对象、选择方法；确定人员、准备材料、将材料提前给评审人员
| SP2.2 | 进行同行评审 Conduct Peer Reviews | 都（进行）参与过哪些同行评审？ Which peer review activities do you participated in? | 提前发材料给评审人员，收集问题、通知评审、会议评审、汇总问题 还可能会问： 正式评审和非正式评审的区别？ 什么是同行？ 同行：对评审对象了解、熟悉，能够提出意见的。同行分技术同行和业务同行
| SP2.3 | 分析同行评审数据 Analyze Peer Review Data | 如何对同行评审的数据进行分析？ How to analyze the data of peer review? | 问题数量、评审时间、效率等数据
Decision Analysis and Resolution
| SP1.1 | 建立决策分析的指南 Establish Guidelines for Decision Analysis | 为什么要建立决策分析指南？ 哪些问题将要进行决策分析？ Why does the organization to establish the DAR guideline? In which situation do you need to use DAR to make decision? | 1、DAR的目的在于使用正式评估过程，依据已建立的准则评估各种已识别的备选方案，以分析可能的决策； 2、对选择的方案的实施结果有重大影响的情况下，如编程语言等的选择，才选择用决策分析
| SP1.2 | 建立评价准则 Establish Evaluation Criteria | 如何建立评价准则？ How to create the evaluation criteria? | 根据候选方案，结合实际问题，确定准则
| SP1.3 | 标识候选解决方案 Identify Alternative Solutions | 如何识别的候选方案？ 识别了几个候选方案？ How do you identify the alternative solutions? How many alternative solutions are identified? | 1，检索文献资料。 2，识别多种可能的备选解决方案。 3，记录被推荐的的候选解决方案。
| SP1.4 | 选择评价方法 Select Evaluation Methods | 选用了什么评价方法评价候选方案？ Which method do you use to evaluate the alternative solutions? | 典型的评价方法有：1，测试；2，建模与模拟；3，工程分析；4，制造分析；5，成本分析；6，商业机会分析；7，调查；8，基于实地经验和原型的推断；9，最终用户评审和评论；10，专家或专家组提出的判断。 权重法；试验法或测试法
| SP1.5 | 评价候选解决方案 Evaluate Alternative Solutions | 如何进行的决策？ How to make decision? 决策的方法都有哪些？你们平时使用哪种方法最多？ | 1，使用已建立的准则和方法，评价备选解决方案。 2，通过项目组头脑风暴对候选方案进行打分
| SP1.6 | 选择解决方案 Select Solutions | 最终选择的方案是怎么做决定的？ 如何考虑了选择的方案相关的风险？ How to select the final solution? Do you take the related risks into consideration for selecting this solution? | 依据评估准则，从备选方案中选择解决方案。

## 测试人员 Tester
| 序号 | 实践 | 访谈问题 | 结合自身实际工作的情况来回答 | 文档证据
Product Integration
| SP1.1 | 建立一个集成策略 Establish an Integration Strategy | 在进行集成测试和系统测试之前（不包含验收测试）你需要做哪些准备？ 如：测试计划、测试用例、测试环境、入口和出口准则等。 How do you prepare in advance in order to perform the integration test and system test (excluding acceptance test), ? ex) Test plan, test case, test environment, entry and exit criteria etc.
| SP1.2 | 建立产品集成环境 Establish the Product Integration Environment
| SP1.3 | 建立产品集成步骤和准则 Establish Product Integration Procedures and Criteria
| SP3.1 | 确认集成用的产品构件已经准备就绪 Confirm Readiness of Product Components for Integration | 集成前如何确认过各个构件如何可用？ 如何进行确认的？ Before the integration, do you confirm that whether the components can be used or not?
| SP3.2 | 组装产品构件 Assemble Product Components | 你是怎样进行集成测试和系统测试的？ How do you perform the integration test and the system test?
| SP3.3 | 评价组装的产品构件 Evaluate Assembled Product Components | 你是怎样评价和分析集成测试与系统测试的结果的？ How do you evaluate and analyze the test results of integration test and system test? 集成的结束标志及通过标准是什么？
Verification
| SP1.1 | 选择待验证的工作产品 Select Work Products for Verification | 如何有测试计划？ Do you make the testing plan?
| SP1.2 | 建立验证环境 Establish the Verification Environment | 如何建立测试环境？ How to establish the testing environment
| SP1.3 | 建立验证规程和准则 Establish Verification Procedures and Criteria | 测试的通过准则是什么？ What are the passing criteria for the testing?
| SP3.1 | 进行验证 Perform Verification | 如何具体执行的系统测试？ How to conduct the system testing?
| SP3.2 | 分析验证结果 Analyze Verification Results | 怎样进行测试结果分析？ How to analyze the testing result?
Validation
| SP1.1 | 选择确认的产品 Select Products for Validation | 如何有验收测试计划？ Do you have the acceptance testing plan?
| SP1.2 | 建立确认环境 Establish the Validation Environment | 如何建立验收测试环境？ How do you create the acceptance testing environment?
| SP1.3 | 建立确认规程和准则 Establish Validation Procedures and Criteria | 验收测试的通过准则是什么？ What are the passing criteria for the acceptance testing?
| SP2.1 | 进行确认 Perform Validation | 如何具体执行的验收测试？ How to conduct the acceptance testing?
| SP2.2 | 分析确认结果 Analyze Validation Results | 如何分析验收测试的结果？ How to analyze the acceptance testing result?

## 配置管理 CM
序号 | 实践 | 访谈问题 | CM结合自身实际工作的情况来回答 | 文档证据
SP1.1 | 确定配置项 Identify Configuration Items | 配置项（CI）是如何识别的？ 请列举一些配置项。 How to identify the configuration items(CI)? Can you give me some examples?
SP1.2 | 建立配置管理系统 Establish a Configuration Management System | 使用什么工具建立配置管理库？ Which tool do you use to create the CM library?
配置管理库结构是怎样的？ What is the structure of the CM library?
SP1.3 | 建立并发布基线 Create or Release Baselines | 都建立了哪些基线？ Which baselines do you create?
建立基线的流程是怎样的？ How to create the baseline?
SP2.1 | 跟踪变更需求 Track Change Requests | 需求变更如何跟踪？ 缺陷引起的变更如何跟踪？ How to track the requirement change? If the change was caused by the bug fix, how do you track?
变更影响分析哪些内容？ How to analyze the change impact?
SP2.2 | 控制配置项 Control Configuration Items | 你是如何控制CI变更的？ How to control the CI change?
SP3.1 | 建立配置管理记录 Establish Configuration Management Records | 配置管理需要记录那些内容？ Which configuration records do you create and maintain?
SP3.2 | 进行配置审计 Perform Configuration Audits | 是如何进行配置审计的？ How to do the configuration audit?

## EPG
| 序号 | 实践 | 访谈问题 | EPG结合自身实际工作的情况来回答 | 文档证据
Organizational Process Focus
| SP1.1 | 建立过程的需要 Establish Organizational Process Needs | 过程改进的目标是什么？ 过程改进目标与公司的商业目标有什么联系？ What are the process improvement objectives? What's the relationship between the process improvement objectives and company's business goals?
| SP1.2 | 评估组织的过程 Appraise the Organization’s Processes | 公司做过几次评估？ 都是什么评估？ How many appraisals does the organization do? What are they? 对公司过程/制度方面，与公司目标之间的差异部分，你们是如何进行分析的？
| SP1.3 | 识别组织的过程改进 Identify the Organization's Process Improvements | 过程改进的来源有哪些? Where are the process improvements from?
| SP2.1 | 建立过程行动计划 Establish Process Action Plans | 如何针对过程改进建议建立了具体的行动计划？ 是怎么做过程行动计划的？ Do you create an action plan based on the collected improvement suggestion? How to create the process improvement action plan?
| SP2.2 | 执行过程行动计划 Implement Process Action Plans | 如何监控行动计划的执行的？ How to monitor the implementation of the action plan?
| SP3.1 | 部署组织过程资产 Deploy Organizational Process Assets | 是如何部署组织过程资产的？ How to deploy the process assets?
| SP3.2 | 部署标准过程 Deploy Standard Processes | 标准过程是如何部署到项目中去的？ 当新项目成立后，如何部署流程到项目中？ How to deploy the standard processes to projects? When a new project starts, how to deploy the processes to new projects?
| SP3.3 | 监控执行 Monitor the Implementation | 如何监控标准过程及过程资产在项目中的使用情况？ How to monitor the implementation of the organization's set of standard processes and use of process assets on all projects?
| SP3.4 | 合并过程相关的经验到组织过程资产库中 Incorporate Experiences into Organizational Process Assets | 通过标准过程的实施收集了哪些过程相关的经验？ What lessons learned and experiences are collected by implementing the processes?
Organizational Process Definition
| SP1.1 | 建立标准过程 Establish Standard Processes | 建立了哪些组织标准过程？怎么建立的？ Which standard processes does the org establish? How to establish?
| SP1.2 | 建立生命周期模型描述 Establish Life-Cycle Model Descriptions | 公司建立了哪几个生命周期模型？ Which lifecycle modes does the organization establish?
| SP1.3 | 建立裁剪准则和指南 Establish Tailoring Criteria and Guideline | 裁剪指南定义了什么内容？ What are in the tailoring guideline?
| SP1.4 | 建立组织级度量库 Establish the Organization’s Measurement Repository | 组织级度量库包含哪些度量数据？ 如何使用度量库中的数据？ What kind of measurement data are in the MA repository? How to use these data?
| SP1.5 | 建立组织的过程资产库 Establish the Organization’s Process Asset Library | 组织过程资产库包含哪些内容？ What does the organization PAL include?
| SP1.6 | 建立工作环境标准 Establish Work Environment Standards | 组织工作环境标准包含哪些内容 What does the organization working environment standard contain?
| SP1.7 | 建立团队准则和指南 Establish Rules and Guidelines for Teams | 组织对团队建设有什么准则和指南？ 团队的运作准则是什么？ What rules and guideline does the organization provide for team building？ What principles exist for team running?

## 质量保证 PPQA
序号 | 实践 | 访谈问题 | QA结合自身实际工作的情况来回答 | 文档证据
SP1.1 | 客观的评价过程 Objectively Evaluate Processes | QA如何保证过程的质量 How does QA ensure the process quality? QA如何保证客观性？ QA如何被审计的？都审计哪些？多长时间被审计一次？
SP1.2 | 客观的评价工作产品 Objectively Evaluate Work Products | QA如何保证产品的质量 How does QA ensure the products quality?
如何依据检查单进行检查? Do you audit based on the checklist?
SP2.1 | 沟通并确保不符合问题得到解决 Communicate and Resolve Noncompliance Issues | 不符合问题是如何进行跟踪和解决的？ How to communicate and track the noncompliance issues?
SP2.2 | 建立质量保证活动记录 Establish Records | 有哪些质量保证活动记录？ Which QA records do you maintain? 不符合问题都记录到哪些地方了？

## 培训 OT
序号 | 实践 | 访谈问题 | OT结合自身实际工作的情况来回答 | 文档证据
SP1.1 | 建立战略培训需要 Establish the Strategic Training Needs | 如何建立了中长期培训规划? Do you create the long term training strategy?
SP1.2 | 确定由组织级负责的培训 Determine Which Training Needs Are the Responsibility of the Organization | 如何明确区分了公司负责的培训和单个项目或支持组负责的培训? Do you determine which training needs are the responsibility of the organization and which are left to the individual project or support group?
SP1.3 | 建立组织的战术培训计划 Establish an Organizational Training Tactical Plan | 如何制定年度培训计划? How to make the annual training plan? 年度培训计划包含哪些内容？ What does the annual training plan contain?
SP1.4 | 建立培训能力 Establish Training Capability | 如何建立公司的培训能力？ How to establish the company's training ability?
SP2.1 | 提交培训 Deliver Training | 描述如何进行一次具体的培训？ Please describe that how to conduct a specific training activity?
SP2.2 | 建立培训记录 Establish Training Records | 有哪些培训记录？ Which training records does exist? 员工技能是如何记录和跟踪的？
SP2.3 | 评价培训效果 Assess Training Effectiveness | 怎么评价培训效果？ How to evaluate the training effectiveness?